## December Reminders Issues
Redmine | Type | Reminder Date | Issue Heading | Comments | Status
19290 | Reminder |  | Stopping of rentals being due for re-possessed | Nadeeshani has replied | Awaiting Feedback
22577 |  |  | DLDH/09/13/1092 - Request to change the Vehicle No | Completion sent | Completed
22566 |  |  | LDH/12/16/4632 - Incorrect Credit Value | I have replied (supplier credit value entering) | Awaiting Feedback
22574 |  |  | Engine Number Issue - Urgent Please | Completion sent | Completed
|  |  | Insurance Premiums - Adding an automated Credit Note | A development
20318 | Reminder |  | Receipts entry screen issue | Inprogress / critical | In Progress
|  |  | Accounts Notes in the Web accounts System | Nadeeshani has replied
22540 |  |  | Recovery/Running cases details reports issues - Daily operations urgent plz | Completion sent / No issue | Completed
22351 |  |  | Request to change the Vendor - BLDH/08/16/1645 | Payment Requisition problem also fixed | Completed
21530 |  |  | Application entry saving error - Daily operations urgent plz | Completion sent | Completed
22191 |  |  | Achieved Lending Targets | Completion sent | Completed
22321 |  |  | Confirmation report issue | NIC problem / Completion Sent | Completed
18578 |  |  | Re: COMPLETION : RE: COMPLETION :RE: Balance Transfer Module - Daily operations urgent plz | Testing | Awaiting Feedback
|  |  | Re: Application Entry - Credit officer selection | Re - evaluation of previous development
|  |  | Re: Closing letter | Re - evaluation of previous development
21285 |  |  | NIC number validation - Daily operations urgent plz | Completion sent | Completed
|  |  | NetAsset reports - additions | Update on a modification
|  |  | Re: Lending summary report | Adding drill to the total row is bit time consuming
|  |  | NetAsset system contract number acquisition process | New Development / Discussion
22555 |  |  | Sanction Letter - Issue | Completion sent | Completed
22550 |  |  | RE: BLDH/12/16/1716 - Daily operations Urgent Plz | Replied | Completed
22429 |  |  | RE: NLDH/01/16/1508 - Pricing Issue? | Wrongly entered residual value issue | Awaiting Feedback
22407 |  | 2016-12-08 | Re: CRITICAL ISSUE - NEED YOUR ATTENTION PLZ | Latest excel to be send / insurance premium duplication | Awaiting Feedback
|  | 2016-12-07 | Re: WebAccounts Issue with IE 11/Win 10 | ?
22482 |  |  | LDH/11/16/4618 - Request to remove broker commission amount | Issue is completed, but not yet replied | Completed
22272 | Reminder | 2016-12-06 | Re: SMS Notifications Process | Completed | Completed

## Current Redmine
# | Status | Project | Tracker | Priority | Subject | Assigned to | Author | Start | Due date | % Done | Actual Time | Chargeble Amount | Chargeble Status | Description
22566 | Awaiting Feedback | LAKD | Bug-Defect | Normal | LDH/12/16/4632 - Incorrect Credit Value | Haneef Muhammed | Inoshi Herath | 2016-12-19 | 2016-12-21 | 100 | 0 |  |  | Please check above contract displays an incorrect credit value in Confirmed cases summary report. Please fix this & make me aware why it occurred. Also please see if system has some other contracts with the same issue as well.
22407 | Awaiting Feedback | LAKD | Bug-Defect | Normal | CRITICAL ISSUE - NEED YOUR ATTENTION PLZ | Haneef Muhammed | Tyronne Kaushal | 2016-11-30 | 2016-12-19 | 100 | 0 |  |  | Dear Nuwan, Seems like the said checks are not in place for other payments. Wonder why we need to pinpoint every little issue in system to get them corrected. A user has again managed to disburse a single contract(other payments processing) twice; which means, IN NETASSET SYSTEM, IT ALLOWS TO MAKE A PAYMENT TWICE FOR A SINGLE INVOICE. So unless we manually checks, there is a possibility for such huge error.
22520 | Awaiting Feedback | LAKD | Bug-Defect | Normal | Invoice Generation & Yard vehicles rentals stop | Haneef Muhammed | Tyronne Kaushal | 2016-12-14 | 2016-12-19 | 100 | 0 |  |  | Dear Haneef, Please check that Invoices generation states there are rental due, prior to the date we did last invoice generation routine. This should be due to the rental stopping modification for yard vehicles. Please check if that is the only case here. Also please make me aware how can I directly identify such contracts in this screen because as you may understand, this invoice generation "from date" can never be understood because of this in future as well.
22429 | Awaiting Feedback | LAKD | Bug-Defect | Normal | NLDH/01/16/1508 - Pricing Issue | Haneef Muhammed | Inoshi Herath | 2016-11-30 | 2016-12-23 | 100 | 0 |  |  | Please check above contract is displaying 31 rentals, which is wrong(should be 30). Please do the needful to correct it. Also please make me aware the reason why such issue occurred & please check the complete system for any such errors...
22422 | Pending | LAKD | Bug-Defect | Normal | Receipts Saving Twice Issue | Jithendra Thenuwara | Inoshi Herath | 2016-11-30 | 2016-12-23 | 0 | 0 |  |  | System is having an issue when saving receipts. In some instances, system gets 2 receipts saved for just one click(Save). Please add a system validation to avoid this. Please make me aware about the logic you would use to solve this.
20318 | Pending | LAKD | Bug-Defect | Normal | Receipts entry screen issue | Udara Somathilaka | Jithendra Thenuwara | 2016-05-10 | 2016-12-21 | 0 | 0 |  |  | In some instances when try to save a receipt, after clicking saving confirmation, screen goes blank. Neither receipt number is displayed or it is actually saved. This is very troubling to cashiers since need to go to ledger & see if the entries are actually saved each time. Please do the needful to correct this issue.
21914 | Pending | LAKD | Other | Normal | Re: Fwd: Upgrading Tomcat Version - Daily operations CRITICAL plz | Keshan Theoder | Gimhani Nandasinghe | 2016-10-14 | 2016-11-30 | 80 | 0 |  |  | For your knowledge, such things can be scheduled at system boot-up with windows Task Scheduler :-). Anyway please correct the below remaining issues:- *First major issue is that even-though the service up & running, cheque printing via systems doesn't work until we again restart the service *When it is started, it is not either getting finished or screen getting closed. If we manually close it(even after few minutes), service goes down again??? *Also noticed that you have used an older version method in this upgrade??? As far as I know, after the TomCat 4.0, it is usually run as a service but, please correct me if I'm mistaken, you have dragged the technology backwards? :-[
20763 | To be Checked | LAKD | Modification | Normal | Client details modify - Restrictions | Inoshi Herath | Deepthika Dissanayaka | 2016-08-11 | 2016-12-30 | 100 | 0 |  |  | Please add a restriction in NetAsset system for modifying clients. Modification of client details are enabled in approval levels. Please block it, if that client is having an active contract. Anyway, still "Client Details - Modify" & "Creation of Clients" screens still need to have the modifying ability as usual.
21083 | To be Checked | LAKD | Other | Normal | NetAsset & WebAccounts Systems User Guides | Nadeeshani Silva | Jithendra Thenuwara | 2016-07-20 | 2016-12-22 | 50 | 0 |  |  | As per the meeting we held at our premises on 2016/07/07 & as > agreed, please provide us a proper/completed user guide amended to our > both systems.... >
22149 | To be Checked | LAKD | Bug-Defect | Normal | Arrears report - huge loading time? | Maduranga Jayawardena | Tyronne Kaushal | 2016-11-03 | 2016-12-15 | 100 | 0 |  |  | Dear Jithendra, Please check that this report also is having the generation issue; that it takes a huge time to get loaded. Sometimes it never does. Please check & do the needful to smooth the report generation & also see the possibility of automating this report as well. -- Thank You, Malitha
19290 | To be Discussed | LAKD | Modification | Urgent | Stopping of rentals being due for re-possessed vehicles | Haneef Muhammed | Gimhani Nandasinghe | 2016-01-21 | 2016-12-22 | 80 | 0 |  |  | It has been a requirement in the legal and accounting point of view, that the accruing of rentals to be stopped with effect from the date of re-possession. 1. In the legal point of view , re-possession implies that the agreement between Lakderana and the customer is terminated, therefore, the rentals cannot be accrued thereafter 2. In accounting point of view, when the rentals are accruing, the figures of income, termination losses and provisions are over-stated. Therefore we need to implement this feature of stopping rentals being due for repossessed vehicles with immediate effect and need of this modification is understood and agreed by the Board at today's meeting. The balances of arrears, future capital , and future interest of the relevant case should be transferred to separate ledger accounts. Please communicate this to the developer, and at the meantime, I will let you know the requirement in detail.
22382 | To be Discussed | LAKD | Chargable Jobs | Normal | Insurance Premiums - Adding an automated Credit Note | Inoshi Herath | Inoshi Herath | 2016-11-25 | 2016-12-23 | 0 | 0 | 0 | Quotation To be Sent
21776 | To be Discussed | LAKD | Chargable Jobs | Normal | NetAsset system contract number acquisition process | Haneef Muhammed | Jithendra Thenuwara | 2016-10-04 | 2017-01-31 | 0 | 0 | 0 | Quotation To be Sent | We need a facility to get the Contract number(Facility number)/Reference number more easily in the quickest possible way with the help of just one screen... -User will need to enter just the Client name, NIC & Vehicle number to obtain this reference number, So he/she is able to issue a receipt to a particular client quickly -If possible, it is better if this new reference number is same as the original Finance number sequence we get from Application entry -If this new reference number is somehow different from the original Contract number, need the ability to make a clear link between these 2 numbers before the acquisition of the original contract number from application summary This is just a rough idea about our new requirement. Please send us a proposal in technical & practical perspective to see how we can implement this in NetAsset system. We are expecting a quick reply from you :-)
22115 | To be Discussed | LAKD | Bug-Defect | Normal | Re: Lending summary report | Haneef Muhammed | Haneef Muhammed | 2016-11-01 | 2017-01-31 | 100 | 0 |  |  | "Achieved lending summary" also have this same issue.... On 11/1/2016 4:40 PM, M.U.M.Fernando wrote: > Dear Jithendra, > > "Total number of contracts" column 'Total' field drill isn't > working. Please check...
22152 | To be Discussed | LAKD | Chargable Jobs | Normal | NetAsset reports - additions | Haneef Muhammed | Tyronne Kaushal | 2016-11-03 | 2017-01-31 | 0 | 0 | 0 | Quotation To be Sent | Dear Jithendra, We need few additions to below reports:- (1)Lending summary report -Add 2 new columns as "Actual Re-New Lending"(place between 12th & 13th columns) & "Actual Lending"(place between 4th & 5th columns) -This "actual re-new lending" is the Capital amount minus Closing settlement(if any) of Confirmation report in a Re-New type contract -This "actual lending" is the cumulative values of "Broker lending", "Direct lending", "Actual Re-New lending" & "Actual RF lending" (2)"Achieved Lending Summary" report drill need the below data columns to be added -Branch name, Employee code, Name, Designation, Target Value, Achieved cases(this already in the drill), Capital(this already in the drill), Actual capital(this can be either Broker lending capital, Direct lending capital, Actual Re-New lending capital or Actual RF lending capital), Lead source category (3)Add a new column to display "Actual Credit value"
21905 | To be Discussed | LAKD | Chargable Jobs | Normal | Contracts associated with Vendors | Haneef Muhammed | Deepthika Dissanayaka | 2016-10-13 | 2017-01-31 | 0 | 0 | 0 | Quotation To be Sent | Please provide us a single facility to see such related contracts(numbers linked to ledger) for Vendor & Broker. -Vendor needs to search by Vendor code, Vendor name, NIC, Telephone -Broker needs to search by Broker code, First/Last name, NIC, Mobile no
21022 | To be Discussed | LAKD | Chargable Jobs | Normal | Confirmation Report | Haneef Muhammed | Deepthika Dissanayaka | 2016-07-13 | 2017-01-31 | 0 | 0 | 56000 | Quotation Sent | Please see the below few points. I have attached a report for your easy reference(with colors):- -Change 8th section "Less insurance charges" field(orange) to take the value from 7th section purple colored 'Balance' section -Remove green colored 'Balance' field since it is no longer needed -Now Insurance charges 'Balance'(purple)='Amount'-'Paid' (same as Initial charges & stamp duty) -All red colored fields & purple colored fields needs to be disabled for editing & All red colored field data needs to automatically filled with system entered data *Please implement these first in TEST system & contact me for any further clarifications
22002 | To be Transfered | LAKD | Bug-Defect | Normal | BLDH/04/15/1315 - Termination issue | Udara Somathilaka | Jithendra Thenuwara | 2016-10-24 | 2016-12-23 | 100 | 0 |  |  | A user had reversed above contract from an approval level. Now it display a Closing invoice & Termination ODI which can not be cancelled. Please check.
# | Status | Project | Tracker | Priority | Subject | Assigned to | Author | Start | Due date | % Done | Actual Time | Chargeble Amount | Chargeble Status | Description
22360 | Pending | LAKDAC | Bug-Defect | Normal | Fwd: Web Accounts Error | Amila Sanjaya | Inoshi Herath | 2016-11-23 | 2016-12-21 | 80 | 0 |  |  | As I made you aware time to time, continuously we note that some voucher entries are being duplicated in web accounts once saved. The reason for this circumstance could not be identified. Please look at this matter and provide us a solution. The details of the instances are given in the forwarded mail.
21277 | To be Transfered | LAKDAC | Bug-Defect | Normal | Fwd: Fwd: Error of serial No of VQ201608-00165 | Udara Somathilaka | Gimhani Nandasinghe | 2016-08-10 | 2016-12-23 | 100 | 0 |  |  | we encountered an error with the serial number of the payment voucher raised trough the seylan bank account. the details attached. This particular voucher has captured the serial continuity of the commercial bank account. Please verify and let us know the reason for this discrepancy.

## Testing Issues
21138 | Receipts entry new type - Please process quickly
18578 | TEST system - Balance Transfer Module | Checked the latest issue & updated the redmine.
21791 | List of users | Already Transferred to LAKD test, but WE should test it there